## Sheet1
The Recipe App Tasks |  |  |  |  | Dev Complete Target Date: 10/22/2017
Storyboard / General Task | Screen (if any) | Owner | UI Ready | Assets Ready | Dev Complete | Dev Target Date | UI Target Date
Launch |  | Cesar | X | X | X | 2017-10-15 | 2017-10-15
App Icon |  | Cesar | X | X | X | 2017-10-15 | 2017-10-15
Parse Setup |  | Alex | - | - | X | 2017-10-15 | -
Authentication (with and without FB) |  | Alex | - | - | X | 2017-10-15 | -
Models |  | Vijay | - | - | X | 2017-10-15 | -
Card POC (iCarrousel) |  | Vijay | - | - | X | 2017-10-15 | -
Storyboard Files |  | Cesar | - | - | X | 2017-10-15 | -
Carrousel Reusable Component (XIB-View) |  | Vijay | - | -
Login.storyboard
- | Login | Vijay/Alex | X | X |  |  | 2017-10-15
- | Sign Up | Vijay | X | X |  |  | 2017-10-15
- | Cooking Preference | Cesar | X | X | X | 2017-10-19 | 2017-10-15
- | Add Friends | Cesar | X | X |  | 2017-10-20 | 2017-10-15
- | Select Friends (Native ContactsUI) | Cesar | X | X |  | 2017-10-20 | 2017-10-15
Main.storyboard
- | Home (TabBar) | Alex | X | X |  |  | 2017-10-15
- | Home - Find Tab | Alex | X | X |  |  | 2017-10-15
- | Home - Explore Tab | Alex | X | X |  |  | 2017-10-15
- | Recipe Detail | Vijay |  |  |  |  | 2017-10-15
- | Cookbook Detail | Alex | X |  |  |  | 2017-10-15
Profile.storyboard
- | Profile | Cesar | X |  |  | 2017-10-21 | 2017-10-15
- | Edit Profile | Cesar |  |  |  | 2017-10-22 | 2017-10-15
Cooking.storyboard
- | Cooking Steps (Cards) | Cesar |  |  |  |  | 2017-10-18
- | Share your result | Alex |  |  |  |  | 2017-10-18
CreateRecipe.storyboard
- | Create Recipe | Vijay |  |  |  |  | 2017-10-21
- | Add Step | Vijay |  |  |  |  | 2017-10-21
- | Post Recipe | Alex |  |  |  |  | 2017-10-21